## Blad1
ID | Fixed | Build | Buildnr | commit naam | omschrijving | omschrijving oplossing | datum
1 | True | travel-planner.Build | 28 | Unit test TemperatureService setCountry written | TemperatureService unit tests not working. | Mock voor de HTTP service geschreven. | 2016-12-20
2 | True | travel-planner.Build | 26 | XML reporter junit added | No test outut generated | Karma configuration repaired. | 2016-12-15
3 | True | travel-planner.Build | 16 | Jasmine tests configured | No test output shown, doesn't finish. | Single run flagg added to make finite. | 2016-12-12
4 | True | travel-planner.Build | 14 | TemeperatureService add and injected | TemperatureService not a singleton. | Bootstrapped service correctly. | 2016-12-08
5 | True | travel-planner.Build | 13 | Select persons rewrtitten | Selecting persons amount doesn't reach component. | Variable typo fixed. | 2016-12-08
6 | True | travel-planner.Build | 9 | Added Booking component | Error on ng serve | Imported component correctly. | 2016-11-30
7 | True | travel-planner.Build | 7 | Module generated | Application structure not correct. | Regenerated. | 2016-11-21
8 | False | Travelplanner-back-end-V2.Build | 17 | Database added hotel attributes | Can't alter database with designer. | Not Fixed. | 2016-12-24
9 | False | Travelplanner-back-end-V2.Build | 18 | Database add hotel limit | Can't alter database with designer. | Not Fixed. | 2016-12-24
10 | False | Travelplanner-back-end-V2.Build | 20 | Added Entity Frameworkd and database connection | Database connection not working. | Changed configuration. | 2016-12-30
11 | False | Travelplanner-back-end-V2.Build | 21 | Json serialization bug | Serialization of json not working as expected. | Not Fixed. | 2016-12-31
12 | False | Travelplanner-back-end-V2.Build | 25 | Add Hotel controller and repo | Custom logic not working. | Not Fixed. | 2017-01-01
13 | False | Travelplanner-back-end-V2.Build | 26 | Added basic auth | Authorization not possible. | Not Fixed. | 2017-01-01